## Cover
CAFE
Group 2
| Creator |  | Aung Kaung Moe Chit Paing Soe Ei Pwint Phyo Chyu Yati Win Myat Thwe
| Create Date |  | 2023-02-27
| Last Update Date |  | 2023-04-09
| Role | AKM | CPS | EPP | CY | WMT
| Front End | ● | ● | ● | ● | ●
| Backend | ● |  | ● |  | ●
Company Co., Ltd

## Schedule (Task)
Schedule | CAFE | [9 empty] | Create Date | 2023-02-27
[11 empty] | Update Date | 2023-03-10
| No | Sub | Task | Assign | Estimate Start | Estimate End | Duration | Actual Start | Actual End | Duration | Complete %
| 1 |  | Schedule | ALL | 2023-02-27 | 2023-03-29 | 30 | 2023-02-27 | 2023-04-08 | 40 | 0%
| 2 |  | Japanese Translation | CPS | 2023-03-06 | 2023-03-11 | 5 | 2023-03-06 | 2023-03-11 | 5 | 90%
| 3 |  | Logo Design | CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
| 4 |  | Requirement Definition | WMT | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
| 5 |  | Function List | AKM,EPP,WMT | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
| 6 |  | User
|  | 6-1 | Screen List | AKM,EPP,WMT | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
|  | 6-2 | UI/UX Kit | AKM,EPP | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
|  | 6-3 | User Screen Flow | AKM,CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
Figma
|  | 6-4 | Home Page | AKM | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
|  | 6-5 | Login | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-6 | Sign Up | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-7 | Forget password (getOTP) | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-8 | Forget password (change password) | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-9 | Promotion page | CY,CPS | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-10 | Buy Shop | AKM | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-11 | Shop Payment | AKM | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-12 | Blog Page | AKM | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-13 | Shop Interface | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-14 | User Profile(Dashboard) | CY,CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-15 | Favourite List | CY,CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-16 | Booking(Dashboard) | CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-17 | Order Page (Dashboard) | CY | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-18 | Chat Box(Dashboard) | CY,CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-19 | Shop List | CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-20 | Booking Page | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-21 | Order Page | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-22 | User Guide | WMT | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-23 | Privacy & Policy | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-24 | Log out Popup | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-25 | FAQs | WMT | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-26 | search | AKM | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-27 | WavePayment(4Step) Page-1 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-28 | WavePayment(4Step) Page-2 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-29 | WavePayment(4Step) Page-3 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-30 | WavePayment(4Step) Page-4 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-31 | Cart (PopUp) | EPP | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-32 | Checkout(PopUp) | EPP | 2023-03-05 | 2023-03-06 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 6-33 | OrderConfirm(PopUp) | EPP | 2023-03-06 | 2023-03-06 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 6-34 | Favourite List(PopUp) | AKM | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 6-35 | Confirm(PopUp) | EPP | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-06 | 1 | 100%
|  | 6-36 | KBZPayment(QRcode) | AKM | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-37 | Payment Successful | AKM | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-38 | Seemore(cafe&cakesmenu) | CY | 2023-03-06 | 2023-03-06 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-39 | Seemore(shop) | CY | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-40 | PromotionSeemore(cafe&cakes) | CY | 2023-03-08 | 2023-03-08 | 1 | 2023-03-08 | 2023-03-08 | 1 | 100%
|  | 6-41 | PromotionSeemore(shop) | CY | 2023-03-06 | 2023-03-06 | 1 | 2023-03-06 | 2023-03-06 | 1 | 100%
|  | 6-42 | Menu(ShopInterface) | EPP | 2023-02-07 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-43 | Reviews(Dashboard) | CPS | 2023-03-08 | 2023-03-09 | 2 | 2023-03-08 | 2023-03-09 | 2 | 100%
|  | 6-44 | Setting(Dashboard) | CPS | 2023-03-08 | 2023-03-09 | 2 | 2023-03-08 | 2023-03-09 | 2 | 100%
|  | 6-48 | dashboard(notification) | AKM | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
| 7 |  | Shop
|  | 7-1 | Screen List | AKM,EPP,CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
|  | 7-2 | Shop Screen Flow | WMT | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
Figma
|  | 7-3 | Login | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 7-4 | sale chart | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-5 | Forget Password(get OTP) | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-6 | Forget password (change password) | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-7 | History | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-8 | Order Page | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-9 | Booking | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-10 | Change Information | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-11 | Add & Change Blog | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-12 | Add & Change Menu | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-13 | Message Chart Box | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-14 | Discount & Promotion | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-15 | Renewal Shop | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-16 | notification | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-17 | Gallery | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-18 | menu | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-19 | Theme | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-20 | update menu | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-21 | gallery | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
| 8 |  | Admin
|  | 8-1 | Screen List | AKM,EPP,CY,WMT | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
|  | 8-2 | Admin Screen Flow | CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
Figma
|  | 8-3 | Shop List (Dashboard) | WMT | 2023-03-02 | 2023-03-03 | 1 | 2023-03-02 | 2023-03-03 | 1 | 100%
|  | 8-4 | Login | EPP | 2023-03-02 | 2023-03-03 | 1 | 2023-03-02 | 2023-03-03 | 1 | 100%
|  | 8-5 | User List (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-6 | Message Chat Box (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-7 | Home Slider (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-8 | About (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-9 | Service (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-10 | Customer's Review (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-11 | Choose options & fill | WMT | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 8-12 | Contact Us (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-13 | Theme & Font (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-14 | Privacy & Policy(Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-15 | FAQs(Dashboard) | WMT | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 8-16 | Discount & Promotions (Page 1) | WMT | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 8-17 | Discount & Promotions (Page 2) | WMT | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 8-18 | Footer | WMT | 2023-03-08 | 2023-03-09 | 1 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-19 | Order List(Dashboard) | AKM | 2023-03-08 | 2023-03-09 | 1 | 2023-03-02 | 2023-03-04 | 1 | 100%
| 9 |  | Database Design | CY,WMT | 2023-03-07 | 2023-03-11 | 4 | 2023-03-07 | 2023-03-11 | 4 | 100%
| 10 |  | ER Diagram | CY,WMT | 2023-03-10 | 2023-03-11 | 1 | 2023-03-10 | 2023-03-11 | 1 | 100%
| 11 |  | Frontend
User
|  | 11-1 | Home Page | AKM | 2023-03-11 | 2023-03-13 | 2 | 2023-03-11 | 2023-03-13 | 2 | 100%
|  | 11-2 | Login | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-3 | Sign Up | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-4 | Forget password (getOTP) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-5 | Forget password (change password) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-6 | Promotion shop&product | CY | 2023-03-14 | 2023-03-15 | 1 | 2023-03-13 | 2023-03-16 | 3 | 100%
|  | 11-7 | Promotion product menu | CY | 2023-03-15 | 2023-03-15 | 0 | 2023-03-15 | 2023-03-15 | 0 | 100%
|  | 11-8 | Promotion Shop menu | CY | 2023-03-16 | 2023-03-16 | 0 | 2023-03-16 | 2023-03-16 | 0 | 100%
|  | 11-9 | Buy Shop | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-10 | Blog Page | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-11 | buyShopFillInformation | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-12 | User Profile(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-13 | Favourite List | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-14 | Booking(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 |  |  | 0 | 100%
|  | 11-15 | Order Page (Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-16 | Chat Box(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 |  |  | 0 | 100%
|  | 11-17 | Shop List | CY | 2023-03-17 | 2023-03-17 | 0 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 11-18 | Booking Page | EPP | 2023-03-16 | 2023-03-17 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 11-19 | Order Page | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 11-20 | Privacy & Policy | WMT | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-21 | Log out Popup | WMT | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 11-22 | FAQs | WMT | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-23 | WavePayment(4Step) Page-1 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-24 | WavePayment(4Step) Page-2 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-25 | WavePayment(4Step) Page-3 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-26 | WavePayment(4Step) Page-4 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-27 | Cart (PopUp) | EPP | 2023-03-16 | 2023-03-17 | 1 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 11-28 | Checkout(PopUp) | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-19 | 5 | 100%
|  | 11-29 | OrderConfirm | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-30 | Confirm(PopUp) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 11-31 | KBZPayment | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 11-32 | Payment Successful | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 11-33 | PromotionSeemore(cafe&cakes) | CY,CPS | 2023-03-14 | 2023-03-17 | 3 | 2023-03-14 | 2023-03-17 | 3 | 100%
|  | 11-34 | Menu(ShopInterface) | EPP | 2023-03-16 | 2023-03-17 | 1 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 11-35 | Reviews(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 11-36 | Setting(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-18 | 2023-03-19 | 1 | 100%
|  | 11-37 | UserGuide | WMT | 2023-04-08 | 2023-04-09 | 1 | 2023-04-08 | 2023-04-09 | 1 | 100%
|  | 11-38 | seemore(cafe&cakesmenu) | AKM | 2023-03-20 | 2023-03-21 | 1 | 2023-03-20 | 2023-03-21 | 1 | 100%
|  | 11-39 | Booking | EPP | 2023-03-15 | 2023-03-16 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
| 12 |  | Shop
|  | 12-1 | Login | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 12-2 | sale chart | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 12-3 | Forget Password(get OTP) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 12-4 | Forget password (change password) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 12-5 | History | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 12-6 | Order Page | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 12-7 | Booking | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 12-8 | Change Information | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-9 | Add & Change Blog | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-10 | Add & Change Menu | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 12-11 | Message Chat Box | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 12-12 | Discount & Promotion | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-13 | Renewal Shop | AKM | 2023-03-16 | 2023-03-16 | 0 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-14 | Notification | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-15 | Gallery | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-16 | Menu | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 12-17 | Theme | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 12-18 | Shop Guide | WMT | 2023-04-08 | 2023-04-09 | 1 | 2023-04-08 | 2023-04-09 | 1 | 100%
| 13 |  | Admin
|  | 13-1 | Shop List (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-2 | Login | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 13-3 | User List (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-4 | Message Chat Box (Dashboard) | AKM | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-5 | Home Slider (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-6 | About (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-7 | Service (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-8 | Customer's Review (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-9 | Choose options & fill | AKM | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-10 | Contact Us (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-11 | Theme & Font (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-12 | PrivacyPolicy(Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-13 | FAQs(Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-14 | Discount & Promotions (Page 1) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-15 | Discount & Promotions (Page 2) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-16 | Footer | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
| 14 |  | Backend
User
|  | 14-1 | Login | EPP | 2023-03-20 | 2023-03-21 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 14-2 | Sign Up/ register | EPP | 2023-03-21 | 2023-03-22 | 1 | 2023-03-21 | 2023-03-23 | 3 | 100%
|  | 14-3 | Forgot password | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 14-4 | Logout | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 14-5 | HomePage Slider&Text | WMT | 2023-03-20 | 2023-03-21 | 1 | 2023-03-31 | 2023-04-01 | 1 | 100%
|  | 14-6 | About us | WMT | 2023-03-20 | 2023-03-21 | 1 | 2023-03-31 | 2023-04-01 | 1 | 100%
|  | 14-7 | Services | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-8 | Customer reviews | EPP | 2023-03-25 | 2023-03-26 | 1 | 2023-04-01 | 2023-04-02 | 1 | 100%
|  | 14-09 | Contactus | EPP | 2023-03-23 | 2023-03-24 | 1 | 2023-03-24 | 2023-03-25 | 1 | 100%
|  | 14-10 | Footer | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-11 | Shop header | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-04-04 | 2023-04-05 | 1 | 100%
|  | 14-12 | Trending cafe and food | EPP | 2023-03-20 | 2023-03-21 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-13 | Trending shop | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-14 | Seemore(products) | AKM | 2023-03-23 | 2023-03-24 | 1 | 2023-04-01 | 2023-04-02 | 1 | 100%
|  | 14-15 | Seemore(shops) | EPP | 2023-03-24 | 2023-03-25 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-16 | Promotions | EPP | 2023-03-30 | 2023-03-31 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-17 | Seemore(promotion products) | EPP | 2023-03-24 | 2023-03-25 | 1 | 2023-04-08 | 2023-04-09 | 1 | 100%
|  | 14-18 | Buyshop | AKM | 2023-03-22 | 2023-03-23 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-19 | Buy shop check | AKM | 2023-03-22 | 2023-03-23 | 1 | 2023-03-22 | 2023-03-23 | 1 | 100%
|  | 14-20 | Give shop dashboard | AKM | 2023-03-22 | 2023-03-23 | 1 | 2023-03-22 | 2023-03-23 | 1 | 100%
|  | 14-21 | KBZ pay scan | EPP | 2023-03-30 | 2023-03-31 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-22 | Wave | AKM | 2023-03-25 | 2023-03-26 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-23 | Search | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-24 | Buy products | AKM | 2023-03-24 | 2023-03-25 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-25 | Favourite | AKM | 2023-03-24 | 2023-03-25 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-26 | Cart | AKM | 2023-03-24 | 2023-03-25 | 1 | 2023-03-28 | 2023-04-02 | 5 | 100%
|  | 14-27 | Checkout | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 14-28 | Order confirm | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 14-29 | Calculate distance for delivery | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 14-30 | Comment and like section for blog | WMT | 2023-03-25 | 2023-03-26 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
|  | 14-31 | Dashboard(profile) | EPP | 2023-03-27 | 2023-03-28 | 1 | 2023-03-28 | 2023-03-31 | 3 | 100%
|  | 14-32 | Dashboard(history_order) | AKM | 2023-03-27 | 2023-03-28 | 1 | 2023-04-03 | 2023-04-04 | 1 | 100%
|  | 14-33 | Dashboard(history_booking) | AKM | 2023-03-29 | 2023-03-30 | 1 |  |  | 0 | 100%
|  | 14-34 | Review | EPP | 2023-03-29 | 2023-03-30 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-35 | Setting(change password) | EPP | 2023-03-30 | 2023-03-31 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 14-36 | Contact us email system | EPP | 2023-03-28 | 2023-03-29 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 14-37 | give coin | WMT | 2023-03-28 | 2023-03-29 | 1 |  |  | 0 | 100%
|  | 14-38 | Shop interface promotion menu | AKM | 2023-03-25 | 2023-03-26 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
| 15 |  | Shop
|  | 15-1 | Login | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-03-22 | 2023-03-23 | 1 | 100%
|  | 15-2 | Logout | EPP | 2023-03-26 | 2023-03-27 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 15-3 | Forget Password(get OTP) | EPP | 2023-03-26 | 2023-03-27 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 15-4 | Forget password (change password) | EPP | 2023-03-26 | 2023-03-27 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 15-5 | Sale chart | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-04-04 | 2023-04-05 | 1 | 100%
|  | 15-6 | History | AKM | 2023-03-29 | 2023-03-30 | 1 |  |  | 0 | 100%
|  | 15-7 | Order Page | WMT | 2023-03-29 | 2023-03-30 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 15-8 | Booking | WMT | 2023-03-29 | 2023-03-30 | 1 | 2023-03-24 | 2023-03-25 | 1 | 100%
|  | 15-9 | Change Information | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-03-26 | 2023-03-27 | 1 | 100%
|  | 15-10 | Add & Change Blog | WMT | 2023-03-30 | 2023-03-31 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 15-11 | Add Menu | AKM | 2023-03-29 | 2023-03-30 | 1 | 2023-03-29 | 2023-03-30 | 1 | 100%
|  | 15-13 | Discount | AKM | 2023-03-30 | 2023-03-31 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
|  | 15-14 | Renewal Shop(Dashboard) | WMT | 2023-03-27 | 2023-03-28 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 15-15 | Notification | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 15-16 | Gallery | EPP | 2023-03-28 | 2023-03-29 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 15-17 | Update Menu | AKM | 2023-03-29 | 2023-03-30 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
| 16 |  | Admin
|  | 16-1 | Shop List (Dashboard) | WMT | 2023-03-28 | 2023-03-29 | 1 | 2023-03-24 | 2023-03-25 | 1 | 100%
|  | 16-2 | Login | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 16-3 | User List (Dashboard) | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-04-03 | 2023-04-04 | 1 | 100%
|  | 16-5 | Home Slider (Dashboard) | WMT | 2023-03-22 | 2023-03-22 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 16-6 | About (Dashboard) | AKM | 2023-03-22 | 2023-03-22 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 16-7 | Service (Dashboard) | EPP | 2023-03-22 | 2023-03-22 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 16-8 | Customer's Review (Dashboard) | EPP | 2023-03-23 | 2023-03-24 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 16-9 | Choose options & fill | AKM | 2023-03-25 | 2023-03-26 | 1 | 2023-03-31 | 2023-04-01 | 1 | 100%
|  | 16-10 | Contact Us (Dashboard) | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 16-11 | PrivacyPolicy(Dashboard) | WMT | 2023-03-21 | 2023-03-22 | 1 | 2023-03-21 | 2023-03-22 | 1 | 100%
|  | 16-12 | FAQs(Dashboard) | WMT | 2023-03-21 | 2023-03-22 | 1 | 2023-03-22 | 2023-03-24 | 2 | 100%
|  | 16-15 | Footer | EPP | 2023-03-22 | 2023-03-22 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 16-16 | Logout | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
0%
363
[6 empty] | Month | 12.1
T_CU_Coin
| customer_id | Customer ID
| coin | Coin Balance
| approve_By | Approve By

## Schedule (Person)
Schedule |  | CAFE | [41 empty] | Create Date
[44 empty] | Update Date | 2022-09-22
|  |  | Feb |  | March | [30 empty] | April
| No | Assign | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 1 | Aung Kaung Moe
| 2 | Chit Paing Soe
| 3 | Ei Pwint Phyo
| 4 | Chyu Yati
| 5 | Win Myat Thwe

## Requirement Definition
Requirement_Definition |  | Create Date
|  | Update Date | 2023-08-20 22:17
１.Business Requirement
１−１. System Background
With the hectic schdeule nowadays, sometimes it is hard to go out and buy your favouirite coffee, drinks and foods.With this system, even when you are too busy or too lazy to go out, you can buy any food and drinks without going anywhere and safe from rain and sun.One stop solution place for Couple, for business people,for teenagers who are looking for a place to meet.
１−2.Target Point Of System
This is to gather the all the Coffee Shops in the Yangon in one place and with one click, a user can buy the food,drinks with delievery system. It also helps increasing the sales of the shops.This website target customers include all kind of ages.
１−3.After System Changes Flow
Once this website is developed, Shops can regularly update information on food products without communicatingwith the customers unlike Social Media.Instocks can be seen in real time. Review system encourages them to do better on business. The customers will have information on the shops inthrough the website, can order available food faster and no call is needed. The user can check the delivery and estimated arrival time can be known.
2.Function Definition
2−１.System Definition
With this system, Shops will have a lot of take away orders and it will increase the sales in a way and saves time from taking order. As the online payment system is also used, collectiong the payment is optional. They can decorate their own page depends on their purchased package Limit. With this system, Users have a variety of Shops and Drinks and Food Products to choose from. Cash or return change is no longer needed with online payment.

## Sheet17
m_customers |  | m_products |  | m_brand |  | m_category |  | m_mechants |  | m_pay_acc
id | int(11) | id | int(11) | id | int(11) | id | int(11) | id | int(11) | id | int(11)
c_name | varchar(128) | p_category | int(11) | brand_name | varchar(128) | cat_name | varchar(128) | me_name | varchar(128) | pay_type | varchar(128)
c_email | varchar(128) | p_title | varchar(128) | brand_photo | varchar(128) | del_flg | int(11) | me_email | varchar(128) | pay_number | int(11)
c_password | varchar(256) | p_buy_price | int(11) | del_flg | int(11) | create_date | date | me_password | varchar(256) | del_flg | int(11)
c_address | varchar(128) | p_sell_price | int(11) | create_date | date | update_date | date | me_address | varchar(128) | create_date | date
c_township | int(11) | p_stock | int(11) | update_date | date |  |  | me_township | int(11) | update_date | date
c_region | int(11) | p_des | varchar(2048) |  |  |  |  | me-region | int(11)
c_phone | varchar(14) | p_detail | longtext |  |  | m_sub_category |  | me_phone | varchar(14)
c_profile | varchar(256) | p_discount | int(11) | m_regions |  | id | int(11) | me_profile | varchar(256) | t_order
code | varchar(255) | p_brand | int(11) | id | int(11) | category_id | int(11) | me_shop_name | varchar(128) | id | int(11)
verify | tinyint(4) | p_photo_1 | varchar(256) | name | varchar(255) | sub_category_name | varchar(128) | me_payment_acc | int(11) | customer_id | int(11)
del_flg | int(11) | p_photo_2 | varchar(256) | del_flg | int(11) | del_flg | int(11) | del_flg | int(11) | total_amt | int(11)
create_date | date | p_photo_3 | varchar(256) | create_date | date | create_date | date | create_date | date | address | varchar(256)
update_date | date | p_photo_4 | varchar(256) | update_date | date | update_date | date | update_date | date | township | int(11)
|  | product_rating | int(11) | [6 empty] | region | int(11)
|  | p_sub_category | int(11) | [6 empty] | payment | varchar(128)
t_cart_detail |  | del_flg | int(11) | m_townships |  | t_product_rating_details |  | t_order_detail |  | payment_no | int(11)
id | int(11) | create_date | date | id | int(11) | id | int(11) | id | int(11) | order_done | int(11)
cart_id | int(11) | update_date | date | region_id | int(11) | product_id | int(11) | order_id | int(11) | order_receive_date | date
product_id | int(11) |  |  | name | varchar(255) | customer_id | int(11) | product_id | int(11) | invoice_date | date
del_flg | int(11) | t_cart |  | del_flg | int(11) | rating_no | int(11) | qty | int(11) | del_flg | int(11)
create_date | date | id | int(11) | create_date | date | product_review | varchar(2048) | amt | int(11) | create_date | date
update_date | date | customer_id | int(11) | update_date | date | del_flg | int(11) | del_flg | int(11) | update_date | date
|  | del_flg | int(11) |  |  | create_date | date | create_date | date
|  | create_date | date |  |  | update_date | date | update_date | date
|  | update_date | date

## 要件定義
要件定義 | CAFE |  | 作成日
|  |  | 更新日 | 2023-08-20 22:17
１.ビジネス要件
１−１. システムの背景
| 今日の多忙なスケジュールにより、外に出てコーヒー、飲み物、食べ物を買うことが困難になることがあります。そのため、このシステムがあれば、忙しくて外出するのが面倒な場合でも、どこにも行かなくても安全に食べ物を買うことができます。カップルのためのロマンチックな場所、ビジネスミーティングのための静かな場所 、ティーンエイジャーの写真を撮るのに最適な場所です。 | 目的 /在宅勤務 / カップル / 会社員
１−2.システムの目標
| ヤンゴンのすべてのコーヒー ショップが 1 か所に集められており、ユーザーはクリック しで、デリバリー システムを通じて食品を購入して使用することができます。このシステムにより、喫茶店の売り上げを伸ばし、配達員の収入を増やすことができます。このウェブサイトは、すべての年齢のユーザーを対象としています。 | システムは何を対象とするか
１−3.システム変更後のフロー
| このサイトが導入されると、店舗は通常の顧客とのコミュニケーションを必要とせずに、ソーシャル メディアで食品情報を更新できるようになります。食材の在庫がリアルタイムでわかる。繁忙期はご注文を締め切らせていただく場合がございます。 レビューシステムは、店舗がより良いビジネスを行うことを奨励します。 ユーザーは、お店の情報を 1 か所で入手できます。ユーザー ウェブサイトから直接座席を予約できます。ユーザーは電話をかけなくても、すぐに注文できます。ユーザーが確認できる 配達と到着予定時刻を知ることができます。 | システム導入後の現実世界の変化と効果
2.関数定義
2−１.システム定義
| お客様は店舗に行かなくても、このウェブサイトから注文できます。こうすることで 注文から時間を節約し、売り上げを伸ばす。支払いはユニット単位で行うため、集金の必要はありません。 ショップ インターフェースは自己管理可能なので、自分のページを無制限に装飾できます。 このシステムにより、顧客はさまざまなショップから飲み物や食べ物を選ぶことができます。 単位払い制ですので、返金の必要はありません。購入ポイントは合計購入時間金額に基づいて加算されます。 貯まったポイントは、割引商品の通貨として交換できます。 | 各機能の利点